## Sheet1
Milestones | When |  | Order | Depends on
Business Plan and apply for legal help | July 2013 |  | 1
Incorporation | July 2013 |  | 2 | Business Plan
Backend dev at MVP | August 2013 |  | 3
Entire website MVP | Late August 2013 | : Start - after Backend dev at MVP Duration: 2 weeks | 4 | Backend dev at MVP
Private Alpha Build | Late August 2013 | : Start - after Entire website MVP Duration: 0 | 5 | Entire website MVP
Alpha Testing | Late August 2013 | : Start - after Entire website MVP Duration: 3 weeks | 6
Private Beta Build | September - October 2013 |  | 7 | Alpha Testing
Private Beta Testing | September - December 2013 |  | 8 | Getting 2k Beta
Public Beta Build | December 2013 |  | 9 | Beta Testing
Public Beta Testing | December - August |  | 10
Getting 2k Beta Testers | January 2014 |  | 11
Endorsing a candidate | May 2014 |  | 12
1.0 Release | August 2014 |  | 13 | Public Beta Testing, Validating Users
First Officially Endorsed Stance | August 2014 |  | 14
First Party Platform | November 2014 |  | 15
Cohesive party platform (flexible/nonvolatile) | March 2015 |  | 16
Phone Apps | March 2015 |  | 17
Validating Users | May 2015 |  | 18
Incorporating ads (TBD) | 2015 |  | 19
Packaging political data for candidates | August 2015 |  | 20
Sustainability | May 2016 |  | 21
Running a local candidate | 2016 |  | 22
Impacting an election | 2016 |  | 23
Selling the tool to businesses | 2018 |  | 24
Running a presidential candidate | 2020 |  | 25
User Milestones | When
100 users | September 2013
1,000 users | November 2013
10,000 users | March 2014
100,000 users | May 2014
1,000,000 users | July 2014
1,000 comments | September 2013
1,000,000 comments | March 2014
1,000,000,000 comments | 2016
Phase 1 | now - may 2014
Phase 2 | may 2014 - aug 2015
Phase 3 | aug 2015 - 2016
Phase 4 | 2016 on